## Sheet1
Alex Gorinson
Milestone Name | SPMP completion date | Actual completion date | Reason for missing milestone
SPMP | 2020-06-26 | 2020-06-25 | -
System Test plan | 2020-07-03 | 2020-07-14 | This milestone was missed due to the fact that certain issues and confusion on the author's part on how to complete this section was present. As such, completing this section too more time to ensure that quality of the document was assured.
Homepage | 2020-07-10 | 2020-06-26 | -
About the Website | 2020-07-10 | 2020-07-04 | -
Social Media Section | 2020-07-10 | 2020-07-05 | -
Alphabetical Country Section | 2020-07-14 | 2020-07-09 | -
World Map Section | 2020-07-16 | 2020-07-10 | -
Completed Website | 2020-07-24 | 2020-07-11 | -